## Sheet1
Project: OrangeHRM
Create New Bug (QA) | [7 empty] | Edit Bug (Dev/QA)
Bug ID | 1 | Bug Description | When add user page contains six mandatory input fields which are user role, employee name, status, username, password and confirm password, I am able to add via user role and password to add user |  |  |  |  | Bug ID | 1 | Bug Description | When add user page contains six mandatory input fields which are user role, employee name, status, username, password and confirm password, I am able to add via user role and password to add user
Module | Admin Module |  | Sub Module | User Management Module |  | Type | Functional | Module | Admin Module |  | Sub Module | User Management Module |  | Type | Functional
Severity | High | Priority | High | Founded In | Release 1 | Date Created | 2023-09-02 | Severity | High | Priority | High | Founded In | Release 1 | Fixed In | Release 2
Steps to recreate | 01. Admin-> User Management-> Users 02. Click the ‘Add’ button which is located at the left-hand corner of the ‘Users’ screen. 03. Type User Role and Password 04. Click the ‘Save’ button which is located at the right-hand corner | [6 empty] | Steps to recreate | 01. Admin-> User Management-> Users 02. Click the ‘Add’ button which is located at the left-hand corner of the ‘Users’ screen. 03. Type User Role and Password 04. Click the ‘Save’ button which is located at the right-hand corner
Assigned To | Raj |  | Assigned By | Thushigha |  | Status | New | Assigned To | Raj |  | Assigned By | Thushigha |  | Status | Duplicate
Comments | Expected Result: Only add user, When type user role, employee name, status, username, password and confirm password Actual Result: Add user, When type user role and password | [6 empty] | Date Created | 2023-09-02 |  |  | Date Closed | 2023-11-02
[8 empty] | Comments | Expected Result: Only add user, When type user role, employee name, status, username, password and confirm password Actual Result: Add user, When type user role and password
Attachment
Attachment
Bug Life Cycle
|  |  | Find Bug |  |  |  |  | Closed
Tester
New/Open
Re Open
|  |  | Assigned |  |  |  | Tester
Fixed
Code Fixed
In Progress
Developer
Starts Fixing the Code
|  |  | Rejected |  | Duplicate |  | Rejected | Deferred
Is it Valid?
Is it duplicate?
Is it reproducible?
Is it in Scope?
Is it Fixed?